## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | D.M. 3/2/2020
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | D.M. 3/2/2020
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | D.M. 3/2/2020
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | D.M. 3/2/2020
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | D.M. 3/2/2020
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | D.M. 3/2/2020
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | D.M. 3/2/2020
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | D.M. 3/2/2020
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | D.M. 3/2/2020
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | D.M. 3/2/2020
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | D.M. 3/2/2020
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | D.M. 3/2/2020
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | D.M. 3/2/2020
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | D.M. 3/2/2020
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | D.M. 3/2/2020
In Game Resignation -As a player, I want to be able to resign the game, so I can stop playing. | Given that I am viewing the game, when I decide that I no longer wish to play the game, then I expect there to be an option to resign the game at some time. |  |  | Pass | E.K. 4/1/20
| Given that I am in the game, when I choose to resign, then I expect to be given an info message if the action was successful or unsuccessfull. |  |  | Pass | E.K. 4/1/20
| Given that I am in the game, when I resign, the I expect the game to end. |  |  | Pass | E.K. 4/1/20
| Given that I am in the game, when I decide to resign, the I expect that my decision will be forwarded to my opponent. |  |  | Pass | E.K. 4/1/20
| Given that I am in the empty turn statem when I want to resign, then I will be able to. |  |  | Pass | E.K. 4/1/20
| Given that I am not in the empty turn state, when I want to resign then I must first get into the empty turn state. |  |  | Pass | E.K. 4/1/20
Opponent Forfeit is Win - As a Player, if my opponent resigns the game, I want to win the game because I did not quit. | Given that I am in the game, when my opponent resigns, then I expect to be informed that I have won the game. |  |  | Pass | E.K. 4/1/20
| Given that I am in the game, when I am informed that my opponent has resigned, then I expect to be taken to the end of game screen. |  |  | Pass | E.K. 4/1/20
End of Game - As a Player, I want to know when the game is over, so that I can move on. | Given I am viewing the game when the game ends by any means, then I expect to be informed that the game is over |  |  | Pass | E.K. 4/1/20
| Given that I am viewing the game, when the game ends, then I expect to be told if I won or lost. |  |  | Pass | E.K. 4/1/20
| Given that I am viewing the game, when I am informed that the game has ended, then I expect to be given a means to exit the game and return to the home menu. |  |  | Pass | E.K. 4/1/20
| Given that I am viewing the game, when I am informed that the game has ended, then I expect to be given a means to exit the game and return to the home menu. |  |  | Pass | E.K. 4/1/20
Playing My Turn State - As a player I want to be forced to make the right move and want to be able to backup my moves, so that I can make the right moves. | Given that I am in a game, when it is my turn and only a single jump is available, then I must take the single jump. |  |  | Pass | D.M. 4/1/20
| Given that I am in a game, when it is my turn and a double jump is available, then I must take the double jump. |  |  | Pass | D.M. 4/1/20
| Given that I am in a game, when it is my turn and no jumps are available, I must make a forward diagonal move with a single piece or any diagonal move with a king piece. |  |  | Pass | D.M. 4/1/20
| Given that I am in a game, when it is my turn, I want to be able to complete a turn by moving a piece |  |  | Pass | S.H. 4/1/20
| Given that I am in a game and I have moved a piece I want to be able to submit my turn to make the move official and end my turn. |  |  | Pass | S.H. 4/1/20
| Given that I am in a game and I have moved a piece, I want to be able to backup my turn, so that I can make a different move. |  |  | Pass | S.H. 4/1/20
As a Player, I want to interact with only. My pieces on my turn, so that I cannot move when it is not my turn. | Given that I am in a game, when it is not my turn, then I am unable to make a move. |  |  | Pass | D.M. 4/1/20
| Given that it is not my turn, when I look at the game view, then I can tell that it is not my turn. |  |  | Pass | D.M. 4/1/20
| Given that it is my turn, when I interact with the board, then I am able to make a valid move. |  |  | Pass | D.M. 4/1/20
| Given that it is my turn, when I look at the game view, then I can tell that it is my turn. |  |  | Pass | D.M. 4/1/20
| Given that it is not my turn and the game has not ended, when it has been 5 seconds since I last checked, then I want to check if my opponent has submitted their turn. |  |  | Pass | D.M. 4/1/20
| Given that it is not my turn and the game has not ended, when it becomes my turn, I want to update my game view to show my opponent's move. |  |  | Pass | D.M. 4/1/20
Sign out - As a player, I want to sign out, so that I can leave. | Given that I am signed in, when I want to sign out, then I expect a means to sign out. |  |  | Pass | B.Y 4/1/20
| Given the I am not signed in, when I look at the nav bar, then I do not expect a means to sign out. |  |  | Pass | B.Y 4/1/20
| Given that I am signed in, when I sign out, then I want my username to become available to other users. |  |  | Pass | B.Y 4/1/20
| Given that I am signed in, when I sign outm then my name will no longer be displayed to other players as signed in. |  |  | Pass | B.Y 4/1/20
King Gameplay - As a olayer, I want to be kinged at the right time in a game, so that I can play the amrerican rules. | Given I am playing a game when one of my pieces reaches the end of the board I expect to king the piece and finish the turn. |  |  | Pass | BY, SM, DM, 4/15/20
| Given I am playing a game, when I have a king piece, I expect to be able to make moves and jumps in any direction. |  |  | Pass | BY, SM, DM, 4/15/20
Moves Help - As a Player, I want to see the possible moves that I can make, so that I can make them if I need help. | As a player, when I am in a game and it is my turn, then there is information about the moves I can make. |  |  | Pass | E.K 4/15/20
| As a player when I am in a game, then I can see the number of pieces that I have left. |  |  | Pass | E.K 4/15/20
| As a player, when I am in a game and it is not my turn, then there is no information on the moves that I can make. |  |  | Pass | E.K 4/15/20